## CATP Input
All installs require | Deploy | Variables Based on Project Requirements | Deploy
2.1.1 Access CLI Interface | Y | 2.1.4 Verify Manual network-based installation
2.1.3 Verify Re-Install or Upgrade Software | Y | 2.1.5 Verify USB-based installation of SAOS 10.x
2.1.6 Verify NTP or verify the date and time | Y | 2.1.8 Applying license – Primary License Server
2.1.7 Configuration – Show running | Y | 2.1.9 License Server – primary and backup
2.2.1 Verify SAOS 10.x software version |  | 2.2.3 SNMP v2c Trap Configuration
2.2.8 Create New User Account | Y | 2.2.4 SNMP v2c Inform Configuration
2.2.9 Validate NACM |  | 2.2.5 SNMP v3 Get Configuration | Y
2.2.10 Management - Source IP | Y | 2.2.6 SNMP v3 Trap Configuration | Y
2.2.23 Verify Backup | Y | 2.2.7 SNMP v3 Inform Configuration | Y
|  | 2.2.11 Syslog Setup | Y
2.2.12 TLS profiles
2.2.13 Pkix and TLS- IP host list
2.2.14 Telemetry
2.2.15 RADIUS over TLS configuration
2.2.16 Syslog over TLS configuration
2.2.18 SSH Rekeying Configuration
2.2.19 DNS Client Setup
|  | 2.2.21 DHCPv6 Client Setup | Y
2.2.22 Static Mgmt IPv6 Setup
2.2.25 Configuration – Golden Configuration
2.2.26 Port Flap Detection
2.2.27 Low Latency Bypass (currently only available on 5162)
2.2.29 Dot1X – Authenticator Setup
2.2.30 Set up LLDP Global Config
2.2.36 Built in Trial License
2.2.37 System gNMI Alarm enhancements
3.2.1 Insertion of a FRU
3.2.2 Enable FRU module using CLI
3.2.3 Licence install - CFP2-DCO plugs
3.2.4 Configure CFP2-DCO ports
3.2.5 5171 Front Temperature Sensor – Early Notification of High Temperature
4.1.1 WebGUI – Management of Sessions
******Beginning of CATP Part II******
|  | 2.1.3 ZTP | Y
2.1.4 SZTP
|  | 2.1.5 Verify Re-Install or Upgrade Software | Y
|  | 2.1.6 Verify Manual network-based installation | Y
|  | 2.1.7 Verify USB-based installation of SAOS 10.x | Y
|  | 2.1.8 Verify NTP or verify the date and time | Y
2.1.9 Configuration – Show running
2.1.10 Applying license – Primary License Server
2.1.11 License Server – primary and backup
2.1.12 User Configurable Reg-Id
2.1.13 Manage Active CLI sessions
2.1.14 Reset to factory default
2.2.1 Verify System Power Cycle will maintain the configuration
2.2.2 Verify SAOS 10.x software version
2.2.3 SNMP Setup – Through Netconf/YANG
2.2.4 SNMP Configuration - CLI
2.2.5 SNMP v2c Trap Configuration
2.2.6 SNMP v2c Inform Configuration
2.2.7 SNMP v3 Get Configuration
2.2.8 SNMP v3 Trap Configuration
2.2.9 SNMP v3 Inform Configuration
2.2.10 Create New User Account
2.2.11 Validate NACM
2.2.12 Management - Source IP
2.2.13 Syslog Setup
2.2.14 TLS profiles
2.2.15 Pkix and TLS- IP host list
2.2.16 Telemetry
2.2.17 RADIUS over TLS configuration
2.2.18 Syslog over TLS configuration
2.2.19 SSH Public Key Authentication
2.2.20 SSH Rekeying Configuration
2.2.21 DNS Client Setup
2.2.22 L3 DHCPv4 Relay Setup
2.2.23 DHCPv6 Client Setup
2.2.24 Static Mgmt IPv6 Setup
2.2.25 Verify Backup
2.2.26 Verify Reset to User Config (RTUC)
2.2.27 Configuration – Golden Configuration
2.2.28 Port Flap Detection
2.2.29 Low Latency Bypass (currently only available on 5162)
2.2.30 Dot1X – Supplicant Setup
|  | 2.2.31 Dot1X – Authenticator Setup | y
2.2.32 Set up LLDP Global Config
2.2.33 Verify show LLDP for a Connected Port
2.2.34 Debugging – Log monitoring
2.2.35 Debugging – Port Mirroring
2.2.36 NETCONF – RPC commands
2.2.37 DHCP Options (Client Identifier & User Class Options)
2.2.38 Built in Trial License
2.2.39 System gNMI Alarm enhancements
|  | 3.2.1 Insertion of a FRU | y
3.2.2 Enable FRU module using CLI
3.2.3 Licence install - CFP2-DCO plugs
3.2.4 Configure CFP2-DCO ports
3.2.5 5171 Front Temperature Sensor – Early Notification of High Temperature
4.1 WebGUI
4.1.1 WebGUI – Management of Sessions
5.1.1 Classifiers
5.1.3 LAG Group - Minimum LAG Aggregation Threshold
5.1.4 LAG Group - Minimum LAG Aggregation Threshold
5.1.5 Configuration of EOAM
|  | 5.1.6 Layer 2 Control Protocol | y
5.1.6.1 Scenario 1: L2CP Handling
5.1.6.2 Scenario 2: L2PT (Layer 2 Protocol Tunneling)
5.2.1 Synchronous Ethernet
5.3.1 10MHz/CLK Interface Input
5.3.2 10MHz/CLK Interface Output
5.4.1 Configure Sync Global Parameters
5.4.2 Configure sync PTP global parameters
5.4.3 Configure frequency and phase protection groups
5.4.4 Configure syncE and PTP input references
5.4.5 Add syncE and PTP input references to frequency and phase protection groups
5.4.6 Configure syncE and PTP output references
5.5.1 General Sync Configuration (G.8275.1)
5.5.2 Enable GNSS
5.5.3 Configure G.8275.1 T-GM
5.6.1 Assisted Full Timing Support Configuration
|  | 5.7.1 Configure G.8275.2 T-GM | Y
|  | 5.8.1 Configuration of Service Activation Test Generator. | y
|  | 5.8.2 Configuration of Service Activation Test Reflector | y
5.8.3 SAT testing with inner VLAN ID validation
5.8.4 SAT testing with 1:1 LAG on UNI
5.8.5 SAT events query on syslog server
5.8.6 SAT testing with MPLS LDP transport tunnel
5.8.7 Deleting SAT configurations
5.9.1 Delay Measurement Test
5.9.2 Synthetic Loss Measurement Test
5.9.3 Frame Loss Measurement Test
5.9.4 Loopback Test
5.9.5 Linktrace Test
5.9.6 Configure and verify Static\Manual Remote MEP
5.9.7 L2 Loop Detect
5.9.8 Remote MEP – Deletion of dynamically discovered remote MEP
|  | 5.9.9 MEP Support on QinQ | y
5.7.8.1 Creating Classifier, fp, fd & flow-point transforms (both ingress and egress)
5.7.8.2 Enabling CFM
|  | 5.7.8.3 Verification | y
5.10.1 TWAMP Server and Session Reflector
5.11.1 MPLS-TP Tunnel Configuration
5.11.2 Static MPLS-TP/PW CLI Show Commands
5.11.3 Static MPLS-TP LSP BFD
5.11.4 Configurable BFD session Parameters
5.11.5 LSP BFD CLI Show Commands
|  | 5.11.6 MPLS-TP Static Tunnel – LSP BFD – Hardware acceleration | y
5.12.1 T-LDP
5.12.2 L2VPN configuration
5.12.3 Static L2VPN
5.12.4 HVPLS configuration with PW redundancy
5.12.5 L2VPN OAM
5.12.6 Dynamic PWE with MTU – Ignore MTU Mismatch
5.12.7 Dynamic PWE – Multi-Hop IP BFD
5.12.8 Dynamic PWE – Mac Withdrawal
|  | 5.12.9 Dynamic PWE – WTR | y
5.12.10 Static PWE – Multi-Segmented PWE
5.13.1 FAT PW baseline Lab / Hardware infrastructure
|  | 5.13.2 FAT PW Configuration | y
5.13.3 FAT PW Verification & Results
5.14.1 FAT PW baseline Lab / Hardware infrastructure
5.14.2 FAT PW Configuration
|  | 5.14.3 FAT PW Verification & Results | y
5.15.1 CC-TYPE 4 over PW configuration
5.15.2 CC-Type Verification & Results
5.16.1 L2VPN VPLS over BGP-LU baseline Lab / Hardware infrastructure
5.16.2 Verification & Results
5.17.1 TDM PWE -DS1/E1
5.17.2 TDM PWE – OC3/STM1
5.18.1.1 Create a frame to COS map
5.18.1.2 Create a COS to frame map
5.18.1.3 Add a frame to COS map to a flow point
|  | 5.18.1.4 Add a COS to frame map to a flow point | y
5.18.1.5 Test COS mapping with traffic flow
5.18.2.1 Create a meter profile
5.18.2.2 Define bandwidth calculation mode
5.18.2.3 Attach a meter profile to a flow point
5.18.2.4 Test ingress metering with traffic
5.18.2.5 Test payload calculation mode in ingress metering with traffic
5.18.3 Hierarchical Ingress Metering
|  | 5.18.3.1 Ingress Metering - QoS Flow and QoS meter profile | y
5.18.3.2 Ingress Metering – Parent Flow point Meter
5.18.3.3 Ingress Metering – QoS Flow only
5.18.3.4 Hierarchical Ingress Metering – QoS Flow and Parent Meters
5.18.4 Assigning CoS to Non-conforming Packets
5.18.5.1 Create a scheduler profile
5.18.5.2 Create a queue group profile
5.18.5.3 Create a scheduler instance
5.18.5.4 Create a queue group instance
5.18.5.6 Bind a queue group to a flow point
5.18.5.7 Bind a queue group to a logical port
5.18.5.8 Verify EQoS with traffic
5.18.5.9 Remove EQoS setup
5.18.5.10 Configure Low Latency Optimization on Egress Queue 5
5.18.6 H-EQOS
5.18.7 CoS Treatment of VRF-injected packets
5.19.1 uOLT Management Configuration
5.19.2 Register ONUs
5.19.3 ONU Configuration
5.19.4 Create SLA Profile
5.19.5 uOLT Data Link Configuration, Networks and PON Connections
5.19.6 Traffic flows to ONUs Via uOLT and Vice versa
5.20.1 8.6.X XGS-PON OFF Box Solution
5.21.1 Ethernet Private Line (EPL) configuration support on the ONU
5.21.1.1 uOLT Management Configuration on 5170
5.21.1.2 Register ONUs
5.21.1.3 ONU Configuration
5.21.1.4 Create SLA Profile
5.21.1.5 uOLT Data Link Configuration, Networks and PON Connections
5.21.2 Ethernet Virtual Private Line (EVPL) Service configuration support on the ONU
5.21.2.1 uOLT Management Configuration on 5170
5.21.2.2 Register ONUs
5.21.2.3 ONU Configuration
5.21.2.4 uOLT Data Link Configuration, Networks and PON Connections
5.21.2.5 NNI interface Configuration
5.21.2.6 PON Connection Configuration
5.21.3 ONU-to-ONU Cross Connect
5.21.3.1 uOLT Management Configuration on 5170
5.21.3.2 Register ONUs
5.21.3.3 ONU Configuration
5.21.3.4 Create SLA Profile
5.21.3.5 uOLT Data Link Configuration, Cross connect and PON Connections
5.21.4 ONU Provision using registration ID
5.22.1 uOLT Management Configuration
5.22.2 ONU and UNI Port Configuration
5.22.3 Create SLA Profile
5.22.4 uOLT Data Link Configuration, Networks and PON Connections
5.22.4.1 Data Link Configuration
5.22.4.2 NNI Interface Configuration
5.22.4.3 PON Connection Configuration
5.22.5 Adding Radius Server info on the Authenticator (PON controller):
5.22.6 Radius Server reachability to Authenticator (PON controller)
5.22.7 DHCP Server reachability to L2 DHCP relay Agent (PON controller)
5.23.1 IGMP snooping Config
|  | 5.24 FlexE Introduction | y
5.24.1 Configure a FlexE Client Port
5.24.2 Configure FlexE Network Port
5.24.3 Create a FlexE Group
5.24.4 Create a FlexE Channel
5.24.5 Create a FlexE Cross Connect
5.24.6 L2 FlexE
5.25 Other: ACL, Flood Containment Profile,
5.25.1 Create an access flow
5.25.2 Delete an access flow
5.25.3 IP ACL
5.25.4 Create a flood containment profile
5.25.5 Delete a flood containment profile
5.26 G.8032: Ethernet Ring Protection
5.27 Macsec Encryption
5.27.1 Hop By Hop Mode on 3926
5.27.2 End to End Mode on 3926
5.27.3 End-to-end mode on 5171
5.28 ETTP loopback
|  | 5.29 LLDP support to pick remote management address: | y
|  | 6.1.1 WebGUI – Create IP Interface | y
|  | 6.1.2 WebGUI – Create IS-IS Instance | y
|  | 6.1.3 WebGUI – Enable LDP | y
|  | 6.1.4 WebGUI – Create BGP Instance | Y

## Sheet2 (hidden)
2.1.3 ZTP | 21
2.1.4 SZTP | 21
2.1.5 Verify Re-Install or Upgrade Software | 23
2.1.6 Verify Manual network-based installation | 25
2.1.7 Verify USB-based installation of SAOS 10.x | 26
2.1.8 Verify NTP or verify the date and time | 28
2.1.9 Configuration – Show running | 31
2.1.10 Applying license – Primary License Server | 32
2.1.11 License Server – primary and backup | 34
2.1.12 User Configurable Reg-Id | 36
2.1.13 Manage Active CLI sessions | 37
2.1.14 Reset to factory default | 39
2.2.1 Verify System Power Cycle will maintain the configuration | 40
2.2.2 Verify SAOS 10.x software version | 41
2.2.3 SNMP Setup – Through Netconf/YANG | 42
2.2.4 SNMP Configuration - CLI | 43
2.2.5 SNMP v2c Trap Configuration | 45
2.2.6 SNMP v2c Inform Configuration | 46
2.2.7 SNMP v3 Get Configuration | 48
2.2.8 SNMP v3 Trap Configuration | 49
2.2.9 SNMP v3 Inform Configuration | 51
2.2.10 Create New User Account | 53
2.2.11 Validate NACM | 53
2.2.12 Management - Source IP | 55
2.2.13 Syslog Setup | 56
2.2.14 TLS profiles | 58
2.2.15 Pkix and TLS- IP host list | 59
2.2.16 Telemetry | 61
2.2.17 RADIUS over TLS configuration | 64
2.2.18 Syslog over TLS configuration | 65
2.2.19 SSH Public Key Authentication | 67
2.2.20 SSH Rekeying Configuration | 68
2.2.21 DNS Client Setup | 69
2.2.22 L3 DHCPv4 Relay Setup | 70
2.2.23 DHCPv6 Client Setup | 73
2.2.24 Static Mgmt IPv6 Setup | 75
2.2.25 Verify Backup | 77
2.2.26 Verify Reset to User Config (RTUC) | 79
2.2.27 Configuration – Golden Configuration | 79
2.2.28 Port Flap Detection | 80
2.2.29 Low Latency Bypass (currently only available on 5162) | 82
2.2.30 Dot1X – Supplicant Setup | 82
2.2.31 Dot1X – Authenticator Setup | 84
2.2.32 Set up LLDP Global Config | 85
2.2.33 Verify show LLDP for a Connected Port | 86
2.2.34 Debugging – Log monitoring | 88
2.2.35 Debugging – Port Mirroring | 90
2.2.36 NETCONF – RPC commands | 92
2.2.37 DHCP Options (Client Identifier & User Class Options) | 93
2.2.38 Built in Trial License | 99
2.2.39 System gNMI Alarm enhancements | 101
3.2.1 Insertion of a FRU | 105
3.2.2 Enable FRU module using CLI | 107
3.2.3 Licence install - CFP2-DCO plugs | 107
3.2.4 Configure CFP2-DCO ports | 109
3.2.5 5171 Front Temperature Sensor – Early Notification of High Temperature | 110
4.1 WebGUI | 113
4.1.1 WebGUI – Management of Sessions | 113
5.1.1 Classifiers | 117
5.1.1.1 Create untagged traffic classifier | 118
5.1.1.2 Create single tagged traffic classifier | 119
5.1.1.3 Create double tagged traffic classifier | 120
5.1.2 Flow points and forwarding domains | 124
5.1.2.1 Create a forwarding domain | 124
5.1.2.3 Create a flow point | 127
5.1.3 LAG Group - Minimum LAG Aggregation Threshold | 130
5.1.4 LAG Group - Minimum LAG Aggregation Threshold | 131
5.1.5 Configuration of EOAM | 133
5.1.6 Layer 2 Control Protocol | 134
5.1.6.1 Scenario 1: L2CP Handling | 135
5.1.6.2 Scenario 2: L2PT (Layer 2 Protocol Tunneling) | 139
5.2.1 Synchronous Ethernet | 142
5.3.1 10MHz/CLK Interface Input | 143
5.3.2 10MHz/CLK Interface Output | 144
5.4.1 Configure Sync Global Parameters | 147
5.4.2 Configure sync PTP global parameters | 148
5.4.3 Configure frequency and phase protection groups | 151
5.4.4 Configure syncE and PTP input references | 152
5.4.5 Add syncE and PTP input references to frequency and phase protection groups | 153
5.4.6 Configure syncE and PTP output references | 154
5.5.1 General Sync Configuration (G.8275.1) | 156
5.5.2 Enable GNSS | 158
5.5.3 Configure G.8275.1 T-GM | 160
5.6.1 Assisted Full Timing Support Configuration | 162
5.7.1 Configure G.8275.2 T-GM | 163
5.8.1 Configuration of Service Activation Test Generator. | 165
5.8.2 Configuration of Service Activation Test Reflector | 168
5.8.3 SAT testing with inner VLAN ID validation | 169
5.8.4 SAT testing with 1:1 LAG on UNI | 184
5.8.5 SAT events query on syslog server | 199
5.8.6 SAT testing with MPLS LDP transport tunnel | 201
5.8.7 Deleting SAT configurations | 217
5.9.1 Delay Measurement Test | 220
5.9.2 Synthetic Loss Measurement Test | 227
5.9.3 Frame Loss Measurement Test | 230
5.9.4 Loopback Test | 233
5.9.5 Linktrace Test | 235
5.9.6 Configure and verify Static\Manual Remote MEP | 236
5.9.7 L2 Loop Detect | 243
5.9.8 Remote MEP – Deletion of dynamically discovered remote MEP | 249
5.9.9 MEP Support on QinQ | 251
5.7.8.1 Creating Classifier, fp, fd & flow-point transforms (both ingress and egress) | 252
5.7.8.2 Enabling CFM | 253
5.7.8.3 Verification | 254
5.10.1 TWAMP Server and Session Reflector | 256
5.11.1 MPLS-TP Tunnel Configuration | 258
5.11.2 Static MPLS-TP/PW CLI Show Commands | 262
5.11.3 Static MPLS-TP LSP BFD | 264
5.11.4 Configurable BFD session Parameters | 265
5.11.5 LSP BFD CLI Show Commands | 266
5.11.6 MPLS-TP Static Tunnel – LSP BFD – Hardware acceleration | 268
5.12.1 T-LDP | 274
5.12.2 L2VPN configuration | 276
5.12.3 Static L2VPN | 278
5.12.4 HVPLS configuration with PW redundancy | 280
5.12.5 L2VPN OAM | 281
5.12.6 Dynamic PWE with MTU – Ignore MTU Mismatch | 282
5.12.7 Dynamic PWE – Multi-Hop IP BFD | 285
5.12.8 Dynamic PWE – Mac Withdrawal | 287
5.12.9 Dynamic PWE – WTR | 288
5.12.10 Static PWE – Multi-Segmented PWE | 291
5.13.1 FAT PW baseline Lab / Hardware infrastructure | 294
5.13.2 FAT PW Configuration | 294
5.13.3 FAT PW Verification & Results | 306
5.14.1 FAT PW baseline Lab / Hardware infrastructure | 311
5.14.2 FAT PW Configuration | 312
5.14.3 FAT PW Verification & Results | 316
5.15.1 CC-TYPE 4 over PW configuration | 321
5.15.2 CC-Type Verification & Results | 324
5.16.1 L2VPN VPLS over BGP-LU baseline Lab / Hardware infrastructure | 326
5.16.2 Verification & Results | 332
5.17.1 TDM PWE -DS1/E1 | 334
5.17.2 TDM PWE – OC3/STM1 | 338
5.18.1.1 Create a frame to COS map | 346
5.18.1.2 Create a COS to frame map | 349
5.18.1.3 Add a frame to COS map to a flow point | 351
5.18.1.4 Add a COS to frame map to a flow point | 353
5.18.1.5 Test COS mapping with traffic flow | 355
5.18.2 Ingress Metering | 356
5.18.2.1 Create a meter profile | 357
5.18.2.2 Define bandwidth calculation mode | 359
5.18.2.3 Attach a meter profile to a flow point | 360
5.18.2.4 Test ingress metering with traffic | 362
5.18.2.5 Test payload calculation mode in ingress metering with traffic | 363
5.18.3 Hierarchical Ingress Metering | 363
5.18.3.1 Ingress Metering - QoS Flow and QoS meter profile | 364
5.18.3.2 Ingress Metering – Parent Flow point Meter | 366
5.18.3.3 Ingress Metering – QoS Flow only | 367
5.18.3.4 Hierarchical Ingress Metering – QoS Flow and Parent Meters | 368
5.18.4 Assigning CoS to Non-conforming Packets | 369
5.18.5 Egress QoS | 374
5.18.5.1 Create a scheduler profile | 375
5.18.5.2 Create a queue group profile | 378
5.18.5.3 Create a scheduler instance | 381
5.18.5.4 Create a queue group instance | 383
5.18.5.6 Bind a queue group to a flow point | 385
5.18.5.7 Bind a queue group to a logical port | 386
5.18.5.8 Verify EQoS with traffic | 389
5.18.5.9 Remove EQoS setup | 390
5.18.5.10 Configure Low Latency Optimization on Egress Queue 5 | 390
5.18.6 H-EQOS | 391
5.18.7 CoS Treatment of VRF-injected packets | 400
5.19.1 uOLT Management Configuration | 405
5.19.2 Register ONUs | 408
5.19.3 ONU Configuration | 408
5.19.4 Create SLA Profile | 409
5.19.5 uOLT Data Link Configuration, Networks and PON Connections | 411
5.19.6 Traffic flows to ONUs Via uOLT and Vice versa | 415
5.20.1 8.6.X XGS-PON OFF Box Solution | 415
5.21.1 Ethernet Private Line (EPL) configuration support on the ONU | 428
5.21.1.1 uOLT Management Configuration on 5170 | 429
5.21.1.2 Register ONUs | 431
5.21.1.3 ONU Configuration | 432
5.21.1.4 Create SLA Profile | 433
5.21.1.5 uOLT Data Link Configuration, Networks and PON Connections | 434
5.21.2 Ethernet Virtual Private Line (EVPL) Service configuration support on the ONU | 438
5.21.2.1 uOLT Management Configuration on 5170 | 439
5.21.2.2 Register ONUs | 441
5.21.2.3 ONU Configuration | 442
5.21.2.4 uOLT Data Link Configuration, Networks and PON Connections | 443
5.21.2.5 NNI interface Configuration | 444
5.21.2.6 PON Connection Configuration | 445
5.21.3 ONU-to-ONU Cross Connect | 445
5.21.3.1 uOLT Management Configuration on 5170 | 446
5.21.3.2 Register ONUs | 448
5.21.3.3 ONU Configuration | 449
5.21.3.4 Create SLA Profile | 450
5.21.3.5 uOLT Data Link Configuration, Cross connect and PON Connections | 451
5.21.4 ONU Provision using registration ID | 454
5.22.1 uOLT Management Configuration | 456
5.22.2 ONU and UNI Port Configuration | 458
5.22.3 Create SLA Profile | 458
5.22.4 uOLT Data Link Configuration, Networks and PON Connections | 459
5.22.4.1 Data Link Configuration | 459
5.22.4.2 NNI Interface Configuration | 460
5.22.4.3 PON Connection Configuration | 460
5.22.5 Adding Radius Server info on the Authenticator (PON controller): | 461
5.19.5.1 Step 1: | 461
5.22.5.1 Step 2: | 461
5.22.6 Radius Server reachability to Authenticator (PON controller) | 462
5.22.7 DHCP Server reachability to L2 DHCP relay Agent (PON controller) | 463
5.23.1.1 Dynamic IGMP snooping Config | 465
5.23.1.2 Static IGMP Join Config | 468
5.24 FlexE Introduction | 470
5.24.1 Configure a FlexE Client Port | 470
5.24.2 Configure FlexE Network Port | 472
5.24.3 Create a FlexE Group | 474
5.24.4 Create a FlexE Channel | 475
5.24.5 Create a FlexE Cross Connect | 477
5.24.6 L2 FlexE | 478
5.24.6.1 Layer 2 FlexE Configuration | 479
5.25 Other: ACL, Flood Containment Profile, | 480
5.25.1 Create an access flow | 480
5.25.2 Delete an access flow | 481
5.25.3 IP ACL | 482
5.25.3.1 Creation of Access Profiles | 483
5.25.4 Create a flood containment profile | 485
5.25.5 Delete a flood containment profile | 486
5.26 G.8032: Ethernet Ring Protection | 487
5.27 Macsec Encryption | 491
5.27.1 Hop By Hop Mode on 3926 | 491
5.27.2 End to End Mode on 3926 | 500
5.27.3 End-to-end mode on 5171 | 509
5.28 ETTP loopback | 512
5.29 LLDP support to pick remote management address: | 516
6.1.1 WebGUI – Create IP Interface | 518
6.1.2 WebGUI – Create IS-IS Instance | 521
6.1.3 WebGUI – Enable LDP | 524
6.1.4 WebGUI – Create BGP Instance | 528